## Sheet1
Sr.No | Pages | Developer | Changes | Status
1 | Home Page | Parag | Change logo | done
2 |  |  | Increase social media icon size, add insta remove twitter, | done
3 |  |  | Remove free delivery & returns | done
4 |  |  | Search bar ok | done
5 |  |  | Categories Ok | done
6 |  |  | Finish Login/register process - increase font size | done
7 |  |  | Shop categories - colour black and increase size | done
8 |  |  | Banner will be slider, buttons on banner | done
9 |  |  | Add top 4 categories | done
|  |  | Add new arrivals section after categories | done
11 |  |  | Features - like how we work of Sp products(https://53digital.com/demos/sp-products/)
Kiran 360deg image
Why Kiran Silver - content from SP products and design from blue stone
| Header |  | Remove currency and location
| Product listing page |  | https://demo.hasthemes.com/reid-v1/reid/shop.html
|  |  | Cateory filter option should be given | done
|  |  | Remove quick view | done
| Blogs |  | Remove blogs page | done
| Product details page |  | https://demo.hasthemes.com/reid-v1/reid/product-details.html
|  |  | Related products remove *comment* | done
|  |  | upsell products remove *comment* | done
Product Details from SOW
|  |  | Wishlist | done
|  |  | remove compare product | done
|  |  | Share | done
| Cart Page |  | https://demo.hasthemes.com/reid-v1/reid/cart.html
|  |  | Product | done
|  |  | Price | done
|  |  | Quantity | done
|  |  | weight | ;done
|  |  | Total price | done
|  |  | Coupon code *comment* | done
|  |  | Proceed to checkout - book order | done
|  |  | Book order- customer mail, admin mail | wait
Order will be reflected in My orders - https://demo.hasthemes.com/reid-v1/reid/my-account.html
| My Account Page |  | Remove downloads | done
| Footer |  | Remove Newsletter | done